## Requested Functionality
Date of Request | Functionality / Bugs | Requested By | Priority | Status | Notes
28/08/2019 | Automated searching of key terms in list |  | High | Done | Display separate key terms for each audit team
28/08/2019 | Free text search of records |  | High | Done | Most important feature as terms will change over time
28/08/2019 | Link to Hansard record on website |  | High | Done
28/08/2019 | High level summary of topics in selected date range (e.g. topics, heading, portfolio, minister etc.) |  | High | Done
28/08/2019 | Filter records by date |  | High | Done
28/08/2019 | Email alerts for new records with mention of clients and key terms |  | Low
28/08/2019 | Record has a short summary which can be read in dashboard |  | Medium | Done
28/08/2019 | Sentiment of discussion in record |  | Low | Done
28/08/2019 | Inclusion of Committee information records in Dashboard |  | Low |  | Most preferred out of the low priority items
28/08/2019 | At least three years of records required for in-depth reviews |  | Low
2019-09-11 | Searching for one or more terms in the record |  | High | Done
2019-09-11 | Notes describing the dashboards limitations (e.g. no Motions records) |  | High | Done
30/09/2019 | Better display when no records are returned | Katherine Noack | Low | Not Implementing | Not possible to implement. Not able to display 0 records when no records are returned because there is no data to run calculations on
2019-10-04 | Don't show URL in table as it takes up lots of space and is already included in tooltip | Grace Lum | Low | Done
2019-10-04 | Make it clear on the dashboard that dashboard A shows the first 200 characters, and B shows a three sentence summary | Aaron Steicke | Medium | Done
2019-10-04 | Clicking on most popular subject box filters records and goes to Audit Dashboard | Aaron Steicke | Low | Done
2019-10-04 | Clicking on most popular subject bill filters records, shows bills only, and goes to Audit Dashboard | Aaron Steicke | Low | Partially Complete | Cannot update Proceeding Type filter to Bills only on selection of metric
2019-10-04 | Clicking one of the subjects on the summary dashboard passed the selected subject(s) through to the next dashboard as an action filter | Aaron Steicke | Low | Done
2019-10-04 | Wildcard search or a strict word search | Aaron Steicke, Grace Lum | High | Done | Text search now uses regular expressions. Will provide a short user guide with common regular expressions that will be of use
2019-10-04 | Explain revert button somewhere on the dashboard or add a ‘clear’ button below the Proceeding Type area | Simon Altus | Medium | Done | Revert button explanation added to notes area
2019-10-04 | Visualise discussion of subjects/topics over time to identify "hot" topics or topics that are discussed over a longer period of time | Simon Altus | Medium | Done
2019-10-04 | When searching for a word in the dashboard, that word to appears in bold when you hover over the shortened text field | Simon Altus |  | Not Implementing | Not possible to implement in Tableau
2019-10-04 | Record summary should show text relevant to the searched for term so that the user can better understand context | Simon Altus, Grace Lum |  | Done | Implemented in Record Search Dashboard C for comparison to other text summary approaches
2019-10-04 | New dashboard showing how many different proceeding types there were relating to a particular subject, which portfolios were mentioned subsequently in relation to this subject/proceeding types, and when these proceeding types took place | Jennifer Wu | Medium | Done | Added new "Subject Summary" dashboard giving an overview of Subjects in Hansard records
2019-10-04 | Filtering not working | Hayley Carter | High | Done
2019-10-04 | Inclusion of Committee information records in Dashboard | Hayley Carter |  | To Discuss
2019-10-04 | Apply this dashboard approach to Gazettes | Hayley Carter |  | To Discuss
2019-10-04 | Graph showing most mentioned clients/agencies | Hayley Carter | High | Done | Need to confirm list of clients used to produce database table
2019-10-04 | Add a parameter to switch between displaying number of records and number of days discussed to Summary dashboard | James Baker | Medium | Done | Couldn't get correct calculation for days discussed when using parameter to change measures. Instead created a dual bar chart that shows both Number of Hansard Records and Number of Days Discussed
2019-10-04 | Show stacked bar charts for each subject - coloured by proceeding type | James Baker | Medium | Done
2019-10-04 | Change the grouping/order of fields so users can use the in-built sorting options on the table | James Baker | Low | Done | Sort by subject
2019-10-04 | Show more of the shortened text/text summary e.g. by making rows higher | James Baker | Low | Done | Double height of rows. Hovering mouse over text will also display entire text in tooltip
2019-10-04 | Clicking on the relevant subject will display all Hansard records relating to that subject | Grace Lum | High | Done | Should have been working, but wasn't for some reason in first version published at AGD. Issue is now fixed with current version published
2019-10-09 | Hansard Subject Summary dashboard should show information graphically rather than in a table | Jennifer Wu | Medium | Done | TreeMap implemented that can drill down from Proceeding Type to Portfolio Name for a given Subject
2019-10-09 | Hide Hansard Record column from view in tables |  | Low | Done
23/10/2019 | Use Record Search Dashboard C for text summary option (remove dashboards/tables A and B) |  | Medium | Done
23/10/2019 | Add additional intructions to notes or tooltips explaining TreeMap drill-down functionality |  | Medium | Done | Added to tooltips
23/10/2019 | Dashboards should work with small monitor sizes |  | Medium | Done | Tested with monitor size 1280 x 1024