## Risk Register
Date Raised | Risk Description | Likelihood of the risk occuring | Impact if the risk occurs | Severity (based on key) | Owner (person who will manage the risk) | Mitigating action
2019-08-16 | Team members unable to work on-site | Probable | Minor | 16% | Project Team | Use of Microsoft Teams and conference calls to communicate with clients. The project team will identify what parts of the project can be completed off-site by external team members.
2019-08-16 | Changes in Government department names can cause challenges in conducting analysis | Certain | Moderate | 62% | Project Owner and Project Sponsor | AGD will provide the project team with a list of departments that have changed names. The project team will conduct a data quality check to ensure that all department name changes have been captured.
2019-08-16 | Delays in receiving timely responses and feedback from key stakeholders due to operational commitments | Possible | Moderate | 38% | Project Owner and Project Sponsor | AGD will establish a project reference group to coordinate and manage stakeholder feedback. Andrew Corrigan to escalate any concerns raised by the project team. In the event that the above two mitigation strategies are not working, agreed communication timeframes will be set between AGD staff and the project team.
2019-08-16 | Unable to find an appropriate platform to complete the project that meets confidentiality restrictions | Rare | Extreme | 1% | Project Team | Identify possible platforms early in the project and gain approval from AGD on their use in the project. For example, the use of a platform such as Microsoft Azure.
2019-08-16 | Lack of team member contribution | Unlikely | Moderate | 16% | Project Team | Team members are to update team regularly on their progress, so that lack of contribution/progress is detected early and can be completed by another team member if required to meet project schedule and deliverable deadlines.
2019-08-16 | Scope creep | Possible | Moderate | 38% | Project Team | Update clients with project progress regularly to ensure that it meets their requirements and seek clarification of requirements at the early stages of the project. Clients will be updated on progress at least once a week in person at client meetings, by email or Microsoft Teams.
2019-08-16 | Team member leaving the group | Rare | Extreme | 1% | Project Team | If a team member leaves the project, dashboard functionality may be reduced so that the deliverable deadline can be met
2019-08-16 | Very few debates on the Hansard dataset related to Auditor-General's Department and its clients. | Unlikely | Moderate | 16% | Project Team | Clients are to be updated regularly so that they can be made aware of any issues that could impact on the usefulness of the project.
2019-08-16 | The project team consists of only four team members to conduct the project in a short time frame which may result in some functionality being unable to be delivered | Certain | Moderate | 62% | Project Team | Employ an Agile approach to develop highest priority features first. Use of planning software to keep track of tasks to be completed and deadlines.
2019-08-16 | Data scraping of Hansard web site takes longer then the time allocated | Possible | Major | 50% | Project Team | Employ an Agile approach by building a proof-of-concept process using a smaller set of data. Use of planning software to keep track of tasks to be completed and deadlines. Additional time will be allocated to the early stages of the project that is crucial to the progression of the project.
2019-08-16 | Text analysis development takes longer then the time allocated | Possible | Major | 50% | Project Team | Advanced text analytics will not be completed as part of this project. This will give more time for requested dashboard functionality such as searching, interactivity and the ability to drill-down into data.
2019-08-27 | XML Schema changes for Hansard records | Rare | Major | 1% | Project Team | Scraping code will include XML version check which will provide some kind of alert/message if XML version changes
2019-08-29 | Dashboard performance is slow impacting on its usefullness for audits | Possible | Moderate | 38% | Project Team | Initially develop dashboard with smaller dataset to test performance. Make use of Tableau features which have better performance
2019-10-11 | Unable to integrate text analytics code into Tableau dashboards | Possible | Moderate | 38% | Project Team | Develop text analytics code with aim to integrate into dashboard. If unable to integrate into dashboard approaches of potential use to AGD will be documented in the final report and code committed to GitHub project